## Backlog Features
ID # | Epic / Featureset | Story | Web Title | Risk |  |  |  | Reward |  |  |  | Risk Score | Reward Score | Priority Score | Size | Notes:
|  |  |  | R1 | R2 | R3 | R4 | R1 | R2 | R3 | R4
0.0 | Launcher | As a veteran I want to see an app launch experience so I know the app is loading | None | Risk R1: 0; Reward R1: 1 | 0 | 0.25 | 0 | S | Reward 1: Users know the app is alive when loading - 1 imp x 1 prob
0.1 | Launcher | As a veteran, I want to hard-press my app icon on the homescreen to see and access key features | None | Risk R1: 15; Reward R1: 5 | 3.75 | 1.25 | 3 | M | Risk1: 3DTouch on iOS will not be used (low feature adoption) - 5 imp x 3 prob Reward 1: 3DTouch on iOS will add fast access to key functions - 5 imp x 1 prob
1.0 | Authentication | As a veteran, I want to sign In with DS Logon | Sign In with DS Logon | Risk R1: 12; Risk R2: 10; Reward R1: 15 | 5.5 | 3.75 | 1.4667 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Technical integration could be very difficult - 5 imp x 2 prob Reward 1: Veterans have access to another way to authenticate - 5 imp x 3 prob
1.1 | Authentication | As a veteran, I want to sign in with My HealtheVet | Sign in with My HealtheVet | Risk R1: 12; Risk R2: 10; Reward R1: 15 | 5.5 | 3.75 | 1.4667 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Technical integration could be very difficult - 5 imp x 2 prob Reward 1: Veterans have access to another way to authenticate - 5 imp x 3 prob
1.2 | Authentication | As a veteran, I want to sign in with ID.me | Sign in with ID.me | Risk R1: 12; Risk R2: 10; Reward R1: 15 | 5.5 | 3.75 | 1.4667 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Technical integration could be very difficult - 5 imp x 2 prob Reward 1: Veterans have access to another way to authenticate - 5 imp x 3 prob
1.3 | Authentication | As a veteran, I want to sign Up (Create an ID.me account) | Sign Up (Create an ID.me account) | Risk R1: 12; Risk R2: 15; Reward R1: 6 | 6.75 | 1.5 | 4.5 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Creating new accounts will be more difficult than simply authenticating - 5 imp x 3 prob Reward 1: Veterans have access to another way to create an account - 2 imp x 3 prob
1.4 | Authentication | As a veteran, I want to let FaceID and TouchID log into my account |  | Risk R1: 3; Risk R2: 3; Reward R1: 15 | 1.5 | 3.75 | 0.4 | M | Risk 1: Technical LOE of integrating various passwords - 1 imp x 3 prob Risk 2: Combining three authentication sources under Face/Touch ID could be difficult - 3 imp x 1 prob Reward 1: Signing in will be extremely easy and fast - 5 imp x 3 prob
2.0 | Search and Navigate | As a veteran, I want to search | Search | Risk R1: 10; Reward R1: 3 | 2.5 | 0.75 | 3.3333 | M | Risk 1: Technical LOE of effective search - 2 imp x 5 prob Reward 1: A lot of users rely on search to navigate complex content - 1 imp x 3 prob
2.1 | Search and Navigate | As a veteran, I want to use Siri to find information and access to features within the app | None | 9 | 3 |  |  | 10 | 10 | 4 |  | 3 | 6 | 0.5 | M | Risk 1: Siri adoption/awareness might mean low use - 3 imp x 3 prob Risk 2: LOE required to integrate/adapt key features for use with Siri - 3 imp x 1 prob Reward 1: Opens the breadth of the app to be used with the device's built-in voice recognition capabilities (reserch observation) - 5 imp x 2 prob Reward 2: Expands adoption and experience for disabled veterans with problems grasping the device - 5 imp x 2 prob Reward 3: Expands accessibility and 508 compliance - 2 imp x 2 prob
2.2 | Search and Navigate | As a veteran, I want to navigate with a natural language UI (chat-like) |  | 8 | 10 |  |  | 15 | 10 | 4 |  | 4.5 | 7.25 | 0.62069 | XL | Risk 1: High technical LOE of integrating 4 imp x 2 prob Risk 2: Are required content services compatible? 5 imp x 2 prob Reward 1: Could allow the app to be extremely simple to use with natural language (the system would interpret a range of input and know how to respond) (reserch observation) 5 imp x 3 prob Reward 2: Expands adoption and experience for disabled veterans with problems grasping the device - 5 imp x 2 prob Reward 3: Expands accessibility and 508 compliance - 2 imp x 2 prob
3.1 | Help | As a veteran, I need help (Frequently Asked Questions) | Help (Frequently Asked Questions) | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
3.2 | Help | As a veteran, I want to call the Vets.gov Help Desk | Call the Vets.gov Help Desk | Risk R1: 1; Reward R1: 15; Reward R2: 6 | 0.25 | 5.25 | 0.047619 | S | Risk 1: Technical LOE of integrating with telephony - 1 imp x 1 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately get general help for VA services - 3 imp x 2 prob
3.3 | Help | As a veteran, I want to get help from Veterans Crisis Line (Call) | Get help from Veterans Crisis Line (Call) | Risk R1: 1; Reward R1: 15; Reward R2: 15 | 0.25 | 7.5 | 0.033333 | S | Risk 1: Technical LOE of integrating with telephony - 1 imp x 1 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately speak with Crisis Line agents to receive help - 5 imp x 3 prob
3.11 | Help | As a veteran, I want to get help from Veterans Crisis Line (Facetime) | Get help from Veterans Crisis Line (Call) | Risk R1: 1; Reward R1: 15; Reward R2: 15; Reward R3: 10 | 0.25 | 10 | 0.025 | S | Risk 1: Technical LOE of integrating with telephony - 1 imp x 1 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately speak with Crisis Line agents to receive help - 5 imp x 3 prob Reward 3: Face-to-face conversations provide a visually rich experience - 5 imp x 2 prob
3.4 | Help | As a veteran, I want to get help from Veterans Crisis Line (Text) | Get help from Veterans Crisis Line (Text) | Risk R1: 4; Reward R1: 15; Reward R2: 15 | 1 | 7.5 | 0.13333 | M | Risk 1: Technical LOE of integrating with sms messaging functions - 2 imp x 2 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately text with Crisis Line agents for "asychronous" help - 5 imp x 3 prob
3.5 | Help | As a veteran, I want to get help from Veterans Crisis Line (Chat) | Get help from Veterans Crisis Line (Chat) | Risk R1: 6; Reward R1: 15; Reward R2: 15 | 1.5 | 7.5 | 0.2 | L | Risk 1: Technical LOE of integrating with messaging - 3 imp x 2 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately text with Crisis Line agents for real-time help - 5 imp x 3 prob
3.6 | Help | As a veteran, I want to get help from Veterans Crisis Line (Link to VeteransCrisisLine.net) | Get help from Veterans Crisis Line (Link to VeteransCrisisLine.net ) | Risk R1: 1; Reward R1: 3 | 0.25 | 0.75 | 0.33333 | S | Risk 1: Technical LOE is low - 1 imp x 1 prob Reward 1: Users can directly access to crisis support services - 3 imp x 1 prob
3.7 | Help | As a veteran, I want to view my VA Welcome Kit | Print out your VA Welcome Kit | Risk R1: 3; Reward R1: 15 | 0.75 | 3.75 | 0.2 | L | Risk 1: Technical LOE of integrating with local storage - 1 imp x 3 prob Reward 1: Easy access to the veteran's onboarding info - 5 imp x 3 prob
3.12 | Help | As a veteran, I want to print out your VA Welcome Kit | Print out your VA Welcome Kit | Risk R1: 9; Risk R2: 6; Risk R3: 15; Reward R1: 15 | 7.5 | 3.75 | 2 | L | Risk 1: Technical LOE of integrating with local storage - 3 imp x 3 prob Risk 3: Technical LOE of creating print-ready format - 2 imp x 3 prob Risk 3: Immaturity of printing from mobile device - 3 imp x 5 prob Reward 1: Easy access to the veteran's files to access or print - 5 imp x 3 prob
3.8 | Help | As a veteran, I want to apply for a hard copy Veteran ID Card | Apply for a printed Veteran ID Card | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Not immediately helpful in mobile context - 1 imp x 1 prob Reward 1: Application confirmation could show a temporary card on-screen - 1 imp x 1 prob | bar: Risk R1; Reward R1
3.9 | Help | As a veteran, I want to download my data locally and have easy access to "My Files" | None | Risk R1: 10; Risk R2: 5; Reward R1: 15; Reward R2: 15 | 3.75 | 7.5 | 0.5 | L | Risk 1: Technical LOE of integrating with local storage - 5 imp x 2 prob Risk 2: Potential for data exfiltration or leakage - 5 imp x 1 prob Reward 1: Easy access to the veteran's files to access or print (reserch observation) - 5 imp x 3 prob Reward 2: Offline access to files - 5 imp x 3 prob
3.10 | Help | As a veteran, I want to scan my documents with my phone and store them online (and locally if I choose to) |  | Risk R1: 15; Risk R2: 10; Reward R1: 15; Reward R2: 15 | 6.25 | 7.5 | 0.83333 | XL | Risk 1: Intergrating with the camera app to scan/capture documents effectively - 5 imp x 3 prob Risk 3: Technical LOE of integrating with local storage - 5 imp x 2 prob Reward 1: Makes scanning simple for veterans (reserch observation) - 5 imp x 3 prob Reward 2: Vastly speeds up the justification process with soft copy evidence - 5 imp x 3 prob
4.0 | Disability | As a veteran, I want to see the Disability Benefits Overview | Diability Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.1 | Disability | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.2 | Disability | As a veteran, I want to see how to apply for Disability Benefits | How to Apply for Disability Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.3 | Disability | As a veteran, I want to see conditions | Conditions | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.4 | Disability | As a veteran, I want to track claims and appeals | Track Your Claims and Appeals | Risk R1: 1; Risk R2: 15; Reward R1: 15; Reward R2: 10 | 4 | 6.25 | 0.64 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Risk 2: Technical LOE for producting accurate status - 5 imp x 3 imp Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Experience of peace-of-mind knowing exactly where my claim is - 5 imp x 2 prob
4.4.1.1 | Disability | As a veteran, I want to view files associated with a claim/appeal | Your Claims | Risk R1: 1; Risk R2: 6; Reward R1: 15; Reward R2: 15 | 1.75 | 7.5 | 0.23333 | L | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Risk 2: Technical integration to produce the documents - 3 imp x 2 prob Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Real-time access to claims documents - 5 imp x 3 prob
4.4.1.4 | Disability | As a veteran, I want to save claim files to My Files |  | Risk R1: 3; Risk R2: 6; Reward R1: 15; Reward R2: 9 | 2.25 | 6 | 0.375 | L | Risk 1: Technical LOE of integrating content - 3 imp x 1 prob Risk 2: Technical integration to produce the documents - 3 imp x 2 prob Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Offline access - 3 imp x 3 prob
4.4.1.2 | Disability | As a veteran, I want to upload new files/evidence from my device | Your Claims | Risk R1: 10; Reward R1: 15; Reward R2: 15 | 2.5 | 7.5 | 0.33333 | L | Risk 1: Technical LOE of integrating with local storage - 5 imp x 2 prob Reward 1: Allowing veterans to add files would make the process easier (research observation) - 5 imp x 3 prob Reward 2: Ability to access any file on the device (beyond just the VA app) - 5 imp x 3 prob
4.4.1.3 | Disability | As a veteran, I want to use my camera to upload/scan files/evidence for claims | Your Claims | Risk R1: 15; Risk R2: 10; Reward R1: 15; Reward R2: 9 | 6.25 | 6 | 1.0417 | XL | Risk 1: Intergrating with the camera app to scan/capture documents effectively - 5 imp x 3 prob Risk 3: Technical LOE of integrating with local storage - 5 imp x 3 prob Reward 1: Makes scanning simple for veterans - 5 imp x 3 prob Reward 2: Shortens the document upload process (restricted to claims) - 3 imp x 3 prob
4.4.2 | Disability | As a veteran, I want to see the details of my claim/appeal | Your Claims | Risk R1: 1; Risk R2: 6; Reward R1: 15; Reward R2: 9 | 1.75 | 6 | 0.29167 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Risk 2: Integration with claims system for status information - 2 imp x 3 prob Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Real-time access to status of claims - 3 imp x 3 prob
4.5 | Disability | As a veteran, I want to learn about the appeals process | Appeals Process | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.6 | Disability | As a veteran, I want to apply for Disabilitty Benefits (eBenefits) | Apply for Disabilitty Benefits (eBenefits) | [8 empty] | 0.25 | 0.25 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.0 | Healthcare | As a veteran, I want to see the Health Care Benefits Overview | Health Care Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.1 | Healthcare | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.2 | Healthcare | As a veteran, I want to learn how to apply for Health Care | How to Apply for Health Care | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.3 | Healthcare | As a veteran, I want to learn about health needs and conditions | Health Needs and Conditions | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.4 | Healthcare | As a veteran, I want to view my prescription refills | Refill Prescriptions | Risk R1: 1; Reward R1: 12 | 0.25 | 3 | 0.083333 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Reward 1: Veterans wanted access to their services (research observation) - 4 imp x 3 prob
5.4.1 | Healthcare | As a veteran, I want to view my past prescriptions refills | Refill Prescriptions | Risk R1: 1; Reward R1: 9 | 0.25 | 2.25 | 0.11111 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Reward 1: Veterans wanted access to their services (research observation) - 3 imp x 3 prob
5.4.2 | Healthcare | As a veteran, I want to refill a prescription | Refill Prescriptions | Risk R1: 2; Reward R1: 15; Reward R2: 15 | 0.5 | 7.5 | 0.066667 | M | Risk 1: Technical LOE of integrating content (to start requests) - 2 imp x 1 prob Reward 1: Veterans wanted access to their services (research observation) - 5 imp x 3 prob Reward 2: Being able to intiate/request services directly through the app - 5 imp x 3 prob
5.5 | Healthcare | As a veteran, I want to see messages in my inbox | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.1 | Healthcare | As a veteran, I want to see messages in my draft messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.2 | Healthcare | As a veteran, I want to see messages in my sent messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.3 | Healthcare | As a veteran, I want to see messages in my deleted messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 9 | 1 | 2.25 | 0.44444 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 3 imp x 3 prob
5.5.4 | Healthcare | As a veteran, I want to see messages in my exam messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.5 | Healthcare | As a veteran, I want to compose message to my Health Care Team | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | M | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob Reward 3: Greatly enhances value-add
5.5.6 | Healthcare | As a veteran, I want to manage my folders | Message Your Health Care Team | Risk R1: 4; Reward R1: 4 | 1 | 1 | 1 | M | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 2 imp x 2 prob
5.5.7 | Healthcare | As a veteran, I want to create a new folder | Message Your Health Care Team | Risk R1: 4; Reward R1: 4 | 1 | 1 | 1 | M | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 2 imp x 2 prob
5.5.8 | Healthcare | As a veteran, I want to email VA using my native email app (instead of the VA app) |  | 15 | 15 | 15 | 3 | 9 | 15 | 6 |  | 12 | 7.5 | 1.6 | XL | Risk 1: Technical integration for a variety of apps/profiles could be high - 5 imp x 3 prob Risk 2: Security and privacy considerations for handling PII are great - 5 imp x 3 prob Risk 3: Lack of control (third party apps and content) - 5 imp x 3 prob Risk 4: Potential exposure of email addresses externally - 3 imp x 1 prob Reward 1: Access to messaging in an app of my choosing - 3 imp x 3 prob Reward 2: Integrating with existing messaging channels - 5 imp x 3 prob Reward 3: Freedom to include any content and attachments - 3 imp x 2 prob
5.6 | Healthcare | As a veteran, I want to view my VA Health Records | Get Your VA Health Records | Risk R1: 10; Reward R1: 2 | 2.5 | 0.5 | 5 | L | Risk 1: Technical LOE of integrating content - 5 imp x 2 prob Reward 1: Veterans wanted easier access to their records (research observation) - 1 imp x 2 prob
5.7 | Healthcare | As a veteran, I want to apply for Health Care Benefits | Apply for Health Care Benefits | Risk R1: 5; Risk R2: 15; Reward R1: 1; Reward R2: 3 | 5 | 1 | 5 | L | Risk 1: Veterans may not need this as much on mobile - 5 imp x 1 prob Risk 3: Technical LOE is likely high (read/write to appointment APIs) - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to start an application - 3 imp x 1 prob
5.8 | Healthcare | As a veteran, I want to view my appointments | Schedule a VA Appointment | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob
5.8.1 | Healthcare | As a veteran, I want to automatically sync my appointments with my device calendar | Schedule a VA Appointment | Risk R1: 15; Reward R1: 15; Reward R2: 10 | 3.75 | 6.25 | 0.6 | XL | Risk 1: Technical LOE of device syncing or installing an account on the device - 5 imp x 3 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob Reward 2: Veterans can get automatic reminders through their native app - 5 imp x 2 prob
5.8.2 | Healthcare | As a veteran, I want view appointment details | Schedule a VA Appointment | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob
5.8.3 | Healthcare | As a veteran, I want to schedule a VA Appointment | Schedule a VA Appointment | Risk R1: 4; Risk R2: 15; Reward R1: 15; Reward R2: 15 | 4.75 | 7.5 | 0.63333 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Risk 2: Technical LOE could be very high - 5 imp x 3 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob Reward 2: Ability to schedule/edit appointments gives the user more freedom - 5 imp x 3 prob
5.9 | Healthcare | As a veteran, I want to learn how to Apply for a Discharge Upgrade | How to Apply for a Discharge Upgrade | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.10 | Healthcare | As a veteran, I want to download my VA Letters to My Files | Download Your VA Letters | Risk R1: 10; Risk R2: 5; Reward R1: 15; Reward R2: 15 | 3.75 | 7.5 | 0.5 | M | Risk 1: Technical LOE of integrating with local storage - 5 imp x 2 prob Risk 2: Potential for data exfiltration or leakage - 5 imp x 1 prob Reward 1: Easy access to the veteran's files to access or print (reserch observation) - 5 imp x 3 prob Reward 2: Offline access to files - 5 imp x 3 prob
5.11 | Healthcare | As a veteran, I want to file a claim for Health Care Benefits |  | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 15 | 4 | 4 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical LOE may be very high - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to start a claim gives the user freedom - 5 imp x 3 prob
6.0 | Education and Training | As a veteran, I want to see the Education and Training Benefits Overview | Education and Training Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.1 | Education and Training | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.2 | Education and Training | As a veteran, I want to learn how to Apply for Education Benefits | How to Apply for Education Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.3 | Education and Training | As a veteran, I want to learn about GI Bill Programs | GI Bill Programs | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.4 | Education and Training | As a veteran, I want to learn about Vocational Rehabilitation & Employment (VR&E) | Vocational Rehabilitation & Employment (VR&E) | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.5 | Education and Training | As a veteran, I want to compare GI Bill Benefits | Compare GI Bill Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.6 | Education and Training | As a veteran, I want to apply for Education and Training Benefits | Apply for Education and Training Benefits | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 15 | 4 | 4 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical LOE may be high - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to start an application gives the user freedom - 5 imp x 3 prob
6.7 | Education and Training | As a veteran, I want to check Post-9/11 GI Bill Benefits | Check Post-9/11 GI Bill Benefits | Risk R1: 1; Risk R2: 9; Reward R1: 1; Reward R2: 10 | 2.5 | 2.75 | 0.90909 | L | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical LOE may be difficult - 3 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Real-time status of benefits - 5 imp x 2 prob
6.8 | Education and Training | As a veteran, I want to check education benefits by school | Check education benefits by school | Risk R1: 1; Risk R2: 9; Reward R1: 1 | 2.5 | 0.25 | 10 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Breaking out schools with sorting/searching/filtering adds level of effort - 3 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob
6.9 | Education and Training | As a veteran, I want to view education benefits by school on a map | Check education benefits by school | 1 | 9 | 9 |  | 1 | 9 |  |  | 4.75 | 2.5 | 1.9 | L | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Breaking out schools with sorting/searching/filtering adds level of effort - 3 imp x 3 prob Risk 3: Technical integration difficult increases - 3 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: A rich visual experience - 3 imp x 3 prob
7.0 | Housing Assistance | As a veteran, I want to see the Housing Assistance Overview | Housing Assistance Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
7.1 | Housing Assistance | As a veteran, I want to learn about Home Loans | Home Loans | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
7.2 | Housing Assistance | As a veteran, I want to learn about Adaptive Housing Grants | Adaptive Housing Grants | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
7.3 | Housing Assistance | As a veteran, I want to apply for a home loan |  | Risk R1: 9; Risk R2: 15; Reward R1: 15 | 6 | 3.75 | 1.6 | XL | Risk 1: Veterans might not want this feature on the app 3 imp x 3 prob Risk 2: Technical LOE will be high - 5 imp x 3 prob Reward 1: Gives the veterans mobile access to services - 5 imp x 3 prob
8.0 | Careers and Employment | As a veteran, I want to see the Careers and Employment Overview | Careers and Employment Overview | Risk R1: 1; Reward R1: 1; Reward R2: 6 | 0.25 | 1.75 | 0.14286 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Older veterans might find these tools more useful than younger vets - 3 imp x 2 prob
8.1 | Careers and Employment | As a veteran, I want to learn about Vocational Rehabilitation & Employment (VR&E) (See 5.4) | Vocational Rehabilitation & Employment (VR&E) (See 5.4) | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
8.2 | Careers and Employment | As a veteran, I want to learn about Small Business Support | Small Business Support | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
8.3 | Careers and Employment | As a veteran, I want to learn about resources for Military and Veteran Family Members | Resources for Military and Veteran Family Members | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.0 | Life Insurance | As a veteran, I want to see the Life Insurance Overview | Life Insurance Overview | [8 empty] | 0.25 | 0.25 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.1 | Life Insurance | As a veteran, I want to learn about Options and Eligibility | Options and Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.2 | Life Insurance | As a veteran, I want more information about Totally Disabled or Terminally Ill | Totally Disabled or Terminally Ill | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.3 | Life Insurance | As a veteran, I want to manage my Life Insurance policy | Managing Your Policy | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 15 | 4 | 4 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical integration/complexity may be very high - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to manage policy gives more freedom - 5 imp x 3 prob
10.0 | Pension | As a veteran, I want to see the Pension Benefits Overview | Pension Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
10.1 | Pension | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
10.2 | Pension | As a veteran, I want to learn how to Apply for a Veterans Pension | How to Apply for a Veterans Pension | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
10.3 | Pension | As a veteran, I want to learn how to Apply for a Survivors Pension | How to Apply for a Survivors Pension | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.0 | Burials and Memorials | As a veteran, I want to see the Burials and Memorials Overview | Burials and Memorials Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.1 | Burials and Memorials | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.2 | Burials and Memorials | As a veteran, I want to plan a burial | Plan a Burial | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 3 | 4 | 1 | 4 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Techincal complexity may be very high - 5 imp x 3 prob Reward 1: Parity with the web site - 1 imp x 1 prob Reward 2: Ability to start the process from mobile - 3 imp x 1 prob
11.3 | Burials and Memorials | As a veteran, I want to plan ahead for my own burial by applying for pre-need eligibility | Plan ahead for your own burial by applying for pre-need eligibility | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 3 | 4 | 1 | 4 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Techincal complexity may be very high - 5 imp x 3 prob Reward 1: Parity with the web site - 1 imp x 1 prob Reward 2: Ability to start the process from mobile - 3 imp x 1 prob
11.4 | Burials and Memorials | As a veteran, I want to learn about allowances and survivor compensation | Allowances and Survivor Compensation | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.5 | Burials and Memorials | As a veteran, I want to find a cemetery | Find a Cemetery | Risk R1: 3; Reward R1: 3 | 0.75 | 0.75 | 1 | M | Risk 1: Technical LOE of building map-based search - 3 imp x 1 prob Reward 1: Filtering/sorting/searching for cemetaries - 1 imp x 3 prob
11.6 | Burials and Memorials | As a veteran, I want to view cemeteries on a map | Find a Cemetery | Risk R1: 5; Reward R1: 9 | 1.25 | 2.25 | 0.55556 | M | Risk 1: Technical LOE of building map-based search - 5 imp x 1 prob Reward 1: map-based search will make searching easier (user observation) - 3 imp x 3 prob
12.0 | Family and Caregiver | As a veteran, I want to learn about family and caregiver benefits | Family and Caregiver Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
13.1 | Facilities | As a veteran, I want to locate facilities and services | Facility and Service Locator | Risk R1: 3; Risk R2: 15; Reward R1: 15; Reward R2: 15 | 4.5 | 7.5 | 0.6 | L | Risk 1: Technical LOE of building location-based searches - 3 imp x 1 prob Risk 2: Data integration with VA services for searching/sorting/filtering could be high - 5 imp x 3 prob Reward 1: map-based search will make searching easier (user observation) - 5 imp x 3 prob Reward 2: Ability to narrow and find facilities and services quickly in ways that make sense to me - 5 imp x 3 prob
13.2 | Facilities | As a veteran, I want to locate facilities and Services on a map | Facility and Service Locator | 3 | 15 |  |  | 15 | 15 | 10 |  | 4.5 | 10 | 0.45 | L | Risk 1: Technical LOE of building map-based search - 3 imp x 1 prob Risk 2: Data integration with VA services for searching/sorting/filtering could be high - 5 imp x 3 prob Reward 1: Map-based search will make searching easier (user observation) - 5 imp x 3 prob Reward 2: Ability to narrow and find facilities and services quickly in ways that make sense to me - 5 imp x 3 prob Reward 3: Ability to expand to service wait-times or other value-add data points per facility - 5 imp x 2 prob
13.3 | Facilities | As a veteran, I want to get navigation directions to a facility using my mapping app |  | Risk R1: 3; Reward R1: 15 | 0.75 | 3.75 | 0.2 | M | Risk 1: Technical LOE with GPS/mapping app - 1 imp x 3 prob Reward 1: Easy ability to find/navigate to the facility - 5 imp x 3 prob
14.0 | Profile | As a veteran, I want to view and edit my vets.gov profile information | Profile and Settings | [8 empty] | 0.25 | 0.25 | 1 | L | Risk 1: May not be needed 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
15.0 | Account Settings | As a veteran, I want to view and edit my account settings | Profile and Settings | [8 empty] | 0.25 | 0.25 | 1 | M | Risk 1: May not be needed 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1

## Sorted Backlog
ID # | Epic / Featureset | Story | Web Title | Risk |  |  |  | Reward |  |  |  | Risk Score | Reward Score | Priority Score | Size | Notes:
|  |  |  | R1 | R2 | R3 | R4 | R1 | R2 | R3 | R4
0.0 | Launcher | As a veteran I want to see an app launch experience so I know the app is loading | None | Risk R1: 0; Reward R1: 1 | 0 | 0.25 | 0 | S | Reward 1: Users know the app is alive when loading - 1 imp x 1 prob
3.11 | Help | As a veteran, I want to get help from Veterans Crisis Line (Facetime) | Get help from Veterans Crisis Line (Call) | Risk R1: 1; Reward R1: 15; Reward R2: 15; Reward R3: 10 | 0.25 | 10 | 0.025 | S | Risk 1: Technical LOE of integrating with telephony - 1 imp x 1 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately speak with Crisis Line agents to receive help - 5 imp x 3 prob Reward 3: Face-to-face conversations provide a visually rich experience - 5 imp x 2 prob
3.3 | Help | As a veteran, I want to get help from Veterans Crisis Line (Call) | Get help from Veterans Crisis Line (Call) | Risk R1: 1; Reward R1: 15; Reward R2: 15 | 0.25 | 7.5 | 0.033333 | S | Risk 1: Technical LOE of integrating with telephony - 1 imp x 1 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately speak with Crisis Line agents to receive help - 5 imp x 3 prob
3.2 | Help | As a veteran, I want to call the Vets.gov Help Desk | Call the Vets.gov Help Desk | Risk R1: 1; Reward R1: 15; Reward R2: 6 | 0.25 | 5.25 | 0.047619 | S | Risk 1: Technical LOE of integrating with telephony - 1 imp x 1 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately get general help for VA services - 3 imp x 2 prob
5.4.2 | Healthcare | As a veteran, I want to refill a prescription | Refill Prescriptions | Risk R1: 2; Reward R1: 15; Reward R2: 15 | 0.5 | 7.5 | 0.066667 | M | Risk 1: Technical LOE of integrating content (to start requests) - 2 imp x 1 prob Reward 1: Veterans wanted access to their services (research observation) - 5 imp x 3 prob Reward 2: Being able to intiate/request services directly through the app - 5 imp x 3 prob
5.4 | Healthcare | As a veteran, I want to view my prescription refills | Refill Prescriptions | Risk R1: 1; Reward R1: 12 | 0.25 | 3 | 0.083333 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Reward 1: Veterans wanted access to their services (research observation) - 4 imp x 3 prob
5.4.1 | Healthcare | As a veteran, I want to view my past prescriptions refills | Refill Prescriptions | Risk R1: 1; Reward R1: 9 | 0.25 | 2.25 | 0.11111 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Reward 1: Veterans wanted access to their services (research observation) - 3 imp x 3 prob
3.4 | Help | As a veteran, I want to get help from Veterans Crisis Line (Text) | Get help from Veterans Crisis Line (Text) | Risk R1: 4; Reward R1: 15; Reward R2: 15 | 1 | 7.5 | 0.13333 | M | Risk 1: Technical LOE of integrating with sms messaging functions - 2 imp x 2 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately text with Crisis Line agents for "asychronous" help - 5 imp x 3 prob
8.0 | Careers and Employment | As a veteran, I want to see the Careers and Employment Overview | Careers and Employment Overview | Risk R1: 1; Reward R1: 1; Reward R2: 6 | 0.25 | 1.75 | 0.14286 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Older veterans might find these tools more useful than younger vets - 3 imp x 2 prob
3.5 | Help | As a veteran, I want to get help from Veterans Crisis Line (Chat) | Get help from Veterans Crisis Line (Chat) | Risk R1: 6; Reward R1: 15; Reward R2: 15 | 1.5 | 7.5 | 0.2 | L | Risk 1: Technical LOE of integrating with messaging - 3 imp x 2 prob Reward 1: Users can directly connect with Vets.gov - 5 imp x 3 prob Reward 2: Users can immediately text with Crisis Line agents for real-time help - 5 imp x 3 prob
3.7 | Help | As a veteran, I want to view my VA Welcome Kit | Print out your VA Welcome Kit | Risk R1: 3; Reward R1: 15 | 0.75 | 3.75 | 0.2 | L | Risk 1: Technical LOE of integrating with local storage - 1 imp x 3 prob Reward 1: Easy access to the veteran's onboarding info - 5 imp x 3 prob
13.3 | Facilities | As a veteran, I want to get navigation directions to a facility using my mapping app |  | Risk R1: 3; Reward R1: 15 | 0.75 | 3.75 | 0.2 | M | Risk 1: Technical LOE with GPS/mapping app - 1 imp x 3 prob Reward 1: Easy ability to find/navigate to the facility - 5 imp x 3 prob
4.4.1.1 | Disability | As a veteran, I want to view files associated with a claim/appeal | Your Claims | Risk R1: 1; Risk R2: 6; Reward R1: 15; Reward R2: 15 | 1.75 | 7.5 | 0.23333 | L | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Risk 2: Technical integration to produce the documents - 3 imp x 2 prob Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Real-time access to claims documents - 5 imp x 3 prob
5.5 | Healthcare | As a veteran, I want to see messages in my inbox | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.1 | Healthcare | As a veteran, I want to see messages in my draft messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.2 | Healthcare | As a veteran, I want to see messages in my sent messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.4 | Healthcare | As a veteran, I want to see messages in my exam messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob
5.5.5 | Healthcare | As a veteran, I want to compose message to my Health Care Team | Message Your Health Care Team | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | M | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 5 imp x 3 prob Reward 3: Greatly enhances value-add
5.8 | Healthcare | As a veteran, I want to view my appointments | Schedule a VA Appointment | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob
5.8.2 | Healthcare | As a veteran, I want view appointment details | Schedule a VA Appointment | Risk R1: 4; Reward R1: 15 | 1 | 3.75 | 0.26667 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob
4.4.2 | Disability | As a veteran, I want to see the details of my claim/appeal | Your Claims | Risk R1: 1; Risk R2: 6; Reward R1: 15; Reward R2: 9 | 1.75 | 6 | 0.29167 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Risk 2: Integration with claims system for status information - 2 imp x 3 prob Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Real-time access to status of claims - 3 imp x 3 prob
3.6 | Help | As a veteran, I want to get help from Veterans Crisis Line (Link to VeteransCrisisLine.net) | Get help from Veterans Crisis Line (Link to VeteransCrisisLine.net ) | Risk R1: 1; Reward R1: 3 | 0.25 | 0.75 | 0.33333 | S | Risk 1: Technical LOE is low - 1 imp x 1 prob Reward 1: Users can directly access to crisis support services - 3 imp x 1 prob
4.4.1.2 | Disability | As a veteran, I want to upload new files/evidence from my device | Your Claims | Risk R1: 10; Reward R1: 15; Reward R2: 15 | 2.5 | 7.5 | 0.33333 | L | Risk 1: Technical LOE of integrating with local storage - 5 imp x 2 prob Reward 1: Allowing veterans to add files would make the process easier (research observation) - 5 imp x 3 prob Reward 2: Ability to access any file on the device (beyond just the VA app) - 5 imp x 3 prob
4.4.1.4 | Disability | As a veteran, I want to save claim files to My Files |  | Risk R1: 3; Risk R2: 6; Reward R1: 15; Reward R2: 9 | 2.25 | 6 | 0.375 | L | Risk 1: Technical LOE of integrating content - 3 imp x 1 prob Risk 2: Technical integration to produce the documents - 3 imp x 2 prob Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Offline access - 3 imp x 3 prob
1.4 | Authentication | As a veteran, I want to let FaceID and TouchID log into my account |  | Risk R1: 3; Risk R2: 3; Reward R1: 15 | 1.5 | 3.75 | 0.4 | M | Risk 1: Technical LOE of integrating various passwords - 1 imp x 3 prob Risk 2: Combining three authentication sources under Face/Touch ID could be difficult - 3 imp x 1 prob Reward 1: Signing in will be extremely easy and fast - 5 imp x 3 prob
5.5.3 | Healthcare | As a veteran, I want to see messages in my deleted messages | Message Your Health Care Team | Risk R1: 4; Reward R1: 9 | 1 | 2.25 | 0.44444 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 3 imp x 3 prob
13.2 | Facilities | As a veteran, I want to locate facilities and Services on a map | Facility and Service Locator | 3 | 15 |  |  | 15 | 15 | 10 |  | 4.5 | 10 | 0.45 | L | Risk 1: Technical LOE of building map-based search - 3 imp x 1 prob Risk 2: Data integration with VA services for searching/sorting/filtering could be high - 5 imp x 3 prob Reward 1: Map-based search will make searching easier (user observation) - 5 imp x 3 prob Reward 2: Ability to narrow and find facilities and services quickly in ways that make sense to me - 5 imp x 3 prob Reward 3: Ability to expand to service wait-times or other value-add data points per facility - 5 imp x 2 prob
2.1 | Search and Navigate | As a veteran, I want to use Siri to find information and access to features within the app | None | 9 | 3 |  |  | 10 | 10 | 4 |  | 3 | 6 | 0.5 | M | Risk 1: Siri adoption/awareness might mean low use - 3 imp x 3 prob Risk 2: LOE required to integrate/adapt key features for use with Siri - 3 imp x 1 prob Reward 1: Opens the breadth of the app to be used with the device's built-in voice recognition capabilities (reserch observation) - 5 imp x 2 prob Reward 2: Expands adoption and experience for disabled veterans with problems grasping the device - 5 imp x 2 prob Reward 3: Expands accessibility and 508 compliance - 2 imp x 2 prob
3.9 | Help | As a veteran, I want to download my data locally and have easy access to "My Files" | None | Risk R1: 10; Risk R2: 5; Reward R1: 15; Reward R2: 15 | 3.75 | 7.5 | 0.5 | L | Risk 1: Technical LOE of integrating with local storage - 5 imp x 2 prob Risk 2: Potential for data exfiltration or leakage - 5 imp x 1 prob Reward 1: Easy access to the veteran's files to access or print (reserch observation) - 5 imp x 3 prob Reward 2: Offline access to files - 5 imp x 3 prob
5.10 | Healthcare | As a veteran, I want to download my VA Letters to My Files | Download Your VA Letters | Risk R1: 10; Risk R2: 5; Reward R1: 15; Reward R2: 15 | 3.75 | 7.5 | 0.5 | M | Risk 1: Technical LOE of integrating with local storage - 5 imp x 2 prob Risk 2: Potential for data exfiltration or leakage - 5 imp x 1 prob Reward 1: Easy access to the veteran's files to access or print (reserch observation) - 5 imp x 3 prob Reward 2: Offline access to files - 5 imp x 3 prob
11.6 | Burials and Memorials | As a veteran, I want to view cemeteries on a map | Find a Cemetery | Risk R1: 5; Reward R1: 9 | 1.25 | 2.25 | 0.55556 | M | Risk 1: Technical LOE of building map-based search - 5 imp x 1 prob Reward 1: map-based search will make searching easier (user observation) - 3 imp x 3 prob
5.8.1 | Healthcare | As a veteran, I want to automatically sync my appointments with my device calendar | Schedule a VA Appointment | Risk R1: 15; Reward R1: 15; Reward R2: 10 | 3.75 | 6.25 | 0.6 | XL | Risk 1: Technical LOE of device syncing or installing an account on the device - 5 imp x 3 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob Reward 2: Veterans can get automatic reminders through their native app - 5 imp x 2 prob
13.1 | Facilities | As a veteran, I want to locate facilities and services | Facility and Service Locator | Risk R1: 3; Risk R2: 15; Reward R1: 15; Reward R2: 15 | 4.5 | 7.5 | 0.6 | L | Risk 1: Technical LOE of building location-based searches - 3 imp x 1 prob Risk 2: Data integration with VA services for searching/sorting/filtering could be high - 5 imp x 3 prob Reward 1: map-based search will make searching easier (user observation) - 5 imp x 3 prob Reward 2: Ability to narrow and find facilities and services quickly in ways that make sense to me - 5 imp x 3 prob
2.2 | Search and Navigate | As a veteran, I want to navigate with a natural language UI (chat-like) |  | 8 | 10 |  |  | 15 | 10 | 4 |  | 4.5 | 7.25 | 0.62069 | XL | Risk 1: High technical LOE of integrating 4 imp x 2 prob Risk 2: Are required content services compatible? 5 imp x 2 prob Reward 1: Could allow the app to be extremely simple to use with natural language (the system would interpret a range of input and know how to respond) (reserch observation) 5 imp x 3 prob Reward 2: Expands adoption and experience for disabled veterans with problems grasping the device - 5 imp x 2 prob Reward 3: Expands accessibility and 508 compliance - 2 imp x 2 prob
5.8.3 | Healthcare | As a veteran, I want to schedule a VA Appointment | Schedule a VA Appointment | Risk R1: 4; Risk R2: 15; Reward R1: 15; Reward R2: 15 | 4.75 | 7.5 | 0.63333 | L | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Risk 2: Technical LOE could be very high - 5 imp x 3 prob Reward 1: Veterans wanted easier access to their appointments (research observation) - 5 imp x 3 prob Reward 2: Ability to schedule/edit appointments gives the user more freedom - 5 imp x 3 prob
4.4 | Disability | As a veteran, I want to track claims and appeals | Track Your Claims and Appeals | Risk R1: 1; Risk R2: 15; Reward R1: 15; Reward R2: 10 | 4 | 6.25 | 0.64 | M | Risk 1: Technical LOE of integrating content - 1 imp x 1 prob Risk 2: Technical LOE for producting accurate status - 5 imp x 3 imp Reward 1: Veterans wanted access to their claims and corresponding details (research observation) - 5 imp x 3 prob Reward 2: Experience of peace-of-mind knowing exactly where my claim is - 5 imp x 2 prob
3.10 | Help | As a veteran, I want to scan my documents with my phone and store them online (and locally if I choose to) |  | Risk R1: 15; Risk R2: 10; Reward R1: 15; Reward R2: 15 | 6.25 | 7.5 | 0.83333 | XL | Risk 1: Intergrating with the camera app to scan/capture documents effectively - 5 imp x 3 prob Risk 3: Technical LOE of integrating with local storage - 5 imp x 2 prob Reward 1: Makes scanning simple for veterans (reserch observation) - 5 imp x 3 prob Reward 2: Vastly speeds up the justification process with soft copy evidence - 5 imp x 3 prob
6.7 | Education and Training | As a veteran, I want to check Post-9/11 GI Bill Benefits | Check Post-9/11 GI Bill Benefits | Risk R1: 1; Risk R2: 9; Reward R1: 1; Reward R2: 10 | 2.5 | 2.75 | 0.90909 | L | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical LOE may be difficult - 3 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Real-time status of benefits - 5 imp x 2 prob
3.1 | Help | As a veteran, I need help (Frequently Asked Questions) | Help (Frequently Asked Questions) | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
3.8 | Help | As a veteran, I want to apply for a hard copy Veteran ID Card | Apply for a printed Veteran ID Card | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Not immediately helpful in mobile context - 1 imp x 1 prob Reward 1: Application confirmation could show a temporary card on-screen - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.0 | Disability | As a veteran, I want to see the Disability Benefits Overview | Diability Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.1 | Disability | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.2 | Disability | As a veteran, I want to see how to apply for Disability Benefits | How to Apply for Disability Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.3 | Disability | As a veteran, I want to see conditions | Conditions | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.5 | Disability | As a veteran, I want to learn about the appeals process | Appeals Process | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.6 | Disability | As a veteran, I want to apply for Disabilitty Benefits (eBenefits) | Apply for Disabilitty Benefits (eBenefits) | [8 empty] | 0.25 | 0.25 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.0 | Healthcare | As a veteran, I want to see the Health Care Benefits Overview | Health Care Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.1 | Healthcare | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.2 | Healthcare | As a veteran, I want to learn how to apply for Health Care | How to Apply for Health Care | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.3 | Healthcare | As a veteran, I want to learn about health needs and conditions | Health Needs and Conditions | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.5.6 | Healthcare | As a veteran, I want to manage my folders | Message Your Health Care Team | Risk R1: 4; Reward R1: 4 | 1 | 1 | 1 | M | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 2 imp x 2 prob
5.5.7 | Healthcare | As a veteran, I want to create a new folder | Message Your Health Care Team | Risk R1: 4; Reward R1: 4 | 1 | 1 | 1 | M | Risk 1: Technical LOE of integrating content - 2 imp x 2 prob Reward 1: Veterans wanted easier access to their communication tools (research observation) - 2 imp x 2 prob
5.9 | Healthcare | As a veteran, I want to learn how to Apply for a Discharge Upgrade | How to Apply for a Discharge Upgrade | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
5.11 | Healthcare | As a veteran, I want to file a claim for Health Care Benefits |  | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 15 | 4 | 4 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical LOE may be very high - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to start a claim gives the user freedom - 5 imp x 3 prob
6.0 | Education and Training | As a veteran, I want to see the Education and Training Benefits Overview | Education and Training Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.1 | Education and Training | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.2 | Education and Training | As a veteran, I want to learn how to Apply for Education Benefits | How to Apply for Education Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.3 | Education and Training | As a veteran, I want to learn about GI Bill Programs | GI Bill Programs | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.4 | Education and Training | As a veteran, I want to learn about Vocational Rehabilitation & Employment (VR&E) | Vocational Rehabilitation & Employment (VR&E) | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.5 | Education and Training | As a veteran, I want to compare GI Bill Benefits | Compare GI Bill Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
6.6 | Education and Training | As a veteran, I want to apply for Education and Training Benefits | Apply for Education and Training Benefits | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 15 | 4 | 4 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical LOE may be high - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to start an application gives the user freedom - 5 imp x 3 prob
7.0 | Housing Assistance | As a veteran, I want to see the Housing Assistance Overview | Housing Assistance Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
7.1 | Housing Assistance | As a veteran, I want to learn about Home Loans | Home Loans | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
7.2 | Housing Assistance | As a veteran, I want to learn about Adaptive Housing Grants | Adaptive Housing Grants | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
8.1 | Careers and Employment | As a veteran, I want to learn about Vocational Rehabilitation & Employment (VR&E) (See 5.4) | Vocational Rehabilitation & Employment (VR&E) (See 5.4) | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
8.2 | Careers and Employment | As a veteran, I want to learn about Small Business Support | Small Business Support | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
8.3 | Careers and Employment | As a veteran, I want to learn about resources for Military and Veteran Family Members | Resources for Military and Veteran Family Members | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.0 | Life Insurance | As a veteran, I want to see the Life Insurance Overview | Life Insurance Overview | [8 empty] | 0.25 | 0.25 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.1 | Life Insurance | As a veteran, I want to learn about Options and Eligibility | Options and Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.2 | Life Insurance | As a veteran, I want more information about Totally Disabled or Terminally Ill | Totally Disabled or Terminally Ill | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
9.3 | Life Insurance | As a veteran, I want to manage my Life Insurance policy | Managing Your Policy | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 15 | 4 | 4 | 1 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Technical integration/complexity may be very high - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to manage policy gives more freedom - 5 imp x 3 prob
10.0 | Pension | As a veteran, I want to see the Pension Benefits Overview | Pension Benefits Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
10.1 | Pension | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
10.2 | Pension | As a veteran, I want to learn how to Apply for a Veterans Pension | How to Apply for a Veterans Pension | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
10.3 | Pension | As a veteran, I want to learn how to Apply for a Survivors Pension | How to Apply for a Survivors Pension | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.0 | Burials and Memorials | As a veteran, I want to see the Burials and Memorials Overview | Burials and Memorials Overview | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.1 | Burials and Memorials | As a veteran, I want to see info about eligibility | Eligibility | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.4 | Burials and Memorials | As a veteran, I want to learn about allowances and survivor compensation | Allowances and Survivor Compensation | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
11.5 | Burials and Memorials | As a veteran, I want to find a cemetery | Find a Cemetery | Risk R1: 3; Reward R1: 3 | 0.75 | 0.75 | 1 | M | Risk 1: Technical LOE of building map-based search - 3 imp x 1 prob Reward 1: Filtering/sorting/searching for cemetaries - 1 imp x 3 prob
12.0 | Family and Caregiver | As a veteran, I want to learn about family and caregiver benefits | Family and Caregiver Benefits | [8 empty] | 0.25 | 0.25 | 1 | S | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
14.0 | Profile | As a veteran, I want to view and edit my vets.gov profile information | Profile and Settings | [8 empty] | 0.25 | 0.25 | 1 | L | Risk 1: May not be needed 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
15.0 | Account Settings | As a veteran, I want to view and edit my account settings | Profile and Settings | [8 empty] | 0.25 | 0.25 | 1 | M | Risk 1: May not be needed 1 imp x 1 prob Reward 1: parity with the web site - 1 imp x 1 prob | bar: Risk R1; Reward R1
4.4.1.3 | Disability | As a veteran, I want to use my camera to upload/scan files/evidence for claims | Your Claims | Risk R1: 15; Risk R2: 10; Reward R1: 15; Reward R2: 9 | 6.25 | 6 | 1.0417 | XL | Risk 1: Intergrating with the camera app to scan/capture documents effectively - 5 imp x 3 prob Risk 3: Technical LOE of integrating with local storage - 5 imp x 3 prob Reward 1: Makes scanning simple for veterans - 5 imp x 3 prob Reward 2: Shortens the document upload process (restricted to claims) - 3 imp x 3 prob
1.0 | Authentication | As a veteran, I want to sign In with DS Logon | Sign In with DS Logon | Risk R1: 12; Risk R2: 10; Reward R1: 15 | 5.5 | 3.75 | 1.4667 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Technical integration could be very difficult - 5 imp x 2 prob Reward 1: Veterans have access to another way to authenticate - 5 imp x 3 prob
1.1 | Authentication | As a veteran, I want to sign in with My HealtheVet | Sign in with My HealtheVet | Risk R1: 12; Risk R2: 10; Reward R1: 15 | 5.5 | 3.75 | 1.4667 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Technical integration could be very difficult - 5 imp x 2 prob Reward 1: Veterans have access to another way to authenticate - 5 imp x 3 prob
1.2 | Authentication | As a veteran, I want to sign in with ID.me | Sign in with ID.me | Risk R1: 12; Risk R2: 10; Reward R1: 15 | 5.5 | 3.75 | 1.4667 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Technical integration could be very difficult - 5 imp x 2 prob Reward 1: Veterans have access to another way to authenticate - 5 imp x 3 prob
5.5.8 | Healthcare | As a veteran, I want to email VA using my native email app (instead of the VA app) |  | 15 | 15 | 15 | 3 | 9 | 15 | 6 |  | 12 | 7.5 | 1.6 | XL | Risk 1: Technical integration for a variety of apps/profiles could be high - 5 imp x 3 prob Risk 2: Security and privacy considerations for handling PII are great - 5 imp x 3 prob Risk 3: Lack of control (third party apps and content) - 5 imp x 3 prob Risk 4: Potential exposure of email addresses externally - 3 imp x 1 prob Reward 1: Access to messaging in an app of my choosing - 3 imp x 3 prob Reward 2: Integrating with existing messaging channels - 5 imp x 3 prob Reward 3: Freedom to include any content and attachments - 3 imp x 2 prob
7.3 | Housing Assistance | As a veteran, I want to apply for a home loan |  | Risk R1: 9; Risk R2: 15; Reward R1: 15 | 6 | 3.75 | 1.6 | XL | Risk 1: Veterans might not want this feature on the app 3 imp x 3 prob Risk 2: Technical LOE will be high - 5 imp x 3 prob Reward 1: Gives the veterans mobile access to services - 5 imp x 3 prob
6.9 | Education and Training | As a veteran, I want to view education benefits by school on a map | Check education benefits by school | 1 | 9 | 9 |  | 1 | 9 |  |  | 4.75 | 2.5 | 1.9 | L | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Breaking out schools with sorting/searching/filtering adds level of effort - 3 imp x 3 prob Risk 3: Technical integration difficult increases - 3 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: A rich visual experience - 3 imp x 3 prob
3.12 | Help | As a veteran, I want to print out your VA Welcome Kit | Print out your VA Welcome Kit | Risk R1: 9; Risk R2: 6; Risk R3: 15; Reward R1: 15 | 7.5 | 3.75 | 2 | L | Risk 1: Technical LOE of integrating with local storage - 3 imp x 3 prob Risk 3: Technical LOE of creating print-ready format - 2 imp x 3 prob Risk 3: Immaturity of printing from mobile device - 3 imp x 5 prob Reward 1: Easy access to the veteran's files to access or print - 5 imp x 3 prob
0.1 | Launcher | As a veteran, I want to hard-press my app icon on the homescreen to see and access key features | None | Risk R1: 15; Reward R1: 5 | 3.75 | 1.25 | 3 | M | Risk1: 3DTouch on iOS will not be used (low feature adoption) - 5 imp x 3 prob Reward 1: 3DTouch on iOS will add fast access to key functions - 5 imp x 1 prob
2.0 | Search and Navigate | As a veteran, I want to search | Search | Risk R1: 10; Reward R1: 3 | 2.5 | 0.75 | 3.3333 | M | Risk 1: Technical LOE of effective search - 2 imp x 5 prob Reward 1: A lot of users rely on search to navigate complex content - 1 imp x 3 prob
11.2 | Burials and Memorials | As a veteran, I want to plan a burial | Plan a Burial | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 3 | 4 | 1 | 4 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Techincal complexity may be very high - 5 imp x 3 prob Reward 1: Parity with the web site - 1 imp x 1 prob Reward 2: Ability to start the process from mobile - 3 imp x 1 prob
11.3 | Burials and Memorials | As a veteran, I want to plan ahead for my own burial by applying for pre-need eligibility | Plan ahead for your own burial by applying for pre-need eligibility | Risk R1: 1; Risk R2: 15; Reward R1: 1; Reward R2: 3 | 4 | 1 | 4 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Techincal complexity may be very high - 5 imp x 3 prob Reward 1: Parity with the web site - 1 imp x 1 prob Reward 2: Ability to start the process from mobile - 3 imp x 1 prob
1.3 | Authentication | As a veteran, I want to sign Up (Create an ID.me account) | Sign Up (Create an ID.me account) | Risk R1: 12; Risk R2: 15; Reward R1: 6 | 6.75 | 1.5 | 4.5 | S | Risk 1: Shallow integration could provide a less than ideal experience - 4 imp x 3 prob Risk 2: Creating new accounts will be more difficult than simply authenticating - 5 imp x 3 prob Reward 1: Veterans have access to another way to create an account - 2 imp x 3 prob
5.6 | Healthcare | As a veteran, I want to view my VA Health Records | Get Your VA Health Records | Risk R1: 10; Reward R1: 2 | 2.5 | 0.5 | 5 | L | Risk 1: Technical LOE of integrating content - 5 imp x 2 prob Reward 1: Veterans wanted easier access to their records (research observation) - 1 imp x 2 prob
5.7 | Healthcare | As a veteran, I want to apply for Health Care Benefits | Apply for Health Care Benefits | Risk R1: 5; Risk R2: 15; Reward R1: 1; Reward R2: 3 | 5 | 1 | 5 | L | Risk 1: Veterans may not need this as much on mobile - 5 imp x 1 prob Risk 3: Technical LOE is likely high (read/write to appointment APIs) - 5 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob Reward 2: Ability to start an application - 3 imp x 1 prob
6.8 | Education and Training | As a veteran, I want to check education benefits by school | Check education benefits by school | Risk R1: 1; Risk R2: 9; Reward R1: 1 | 2.5 | 0.25 | 10 | M | Risk 1: Veterans may not need this content as much - 1 imp x 1 prob Risk 2: Breaking out schools with sorting/searching/filtering adds level of effort - 3 imp x 3 prob Reward 1: parity with the web site - 1 imp x 1 prob